1)  Harbor Breeze Corporation

Harbor Breeze management intends to use PERT / CPM analysis to monitor the progress of its new office complex using the following information:

| Task | Duration | Prerequisite Tasks |
| --- | --- | --- |
| A) Site selection | 3 months | None |
| B) Architectural design | 4 months | None |
| C) Closing of old office | 3 months | A |
| D) Construction of new complex | 5 months | A and B |
| E) Move into new complex | 2 months | C and D |

Construct the Harbor Breeze PERT / CPM diagram, determine the minimum project finish time, and identify the critical path.

Solution:

Following the instructions in the associated instructions yields the following diagram.

Answer:  	The minimum project finish time is 11 months and the critical path is B-D-E.

2)  Pamlico Software

Pamlico management will use PERT / CPM analysis to control the development of its new software product, code named "Sea Spray."  The following table contains Sea Spray task information:

| Task | Duration | Prerequisite Tasks |
| --- | --- | --- |
| A) Develop program specifications | 3 months | None |
| B) Create program documentation | 3 months | A |
| C) Implement marketing plan | 2 months | B |
| D) Design program logic | 4 months | None |
| E) Code and translate program | 5 months | A and D |
| F) Test and debug program | 3 months | E |

Construct the PERT / CPM diagram for the Sea Spray project, determine the minimum project finish time, and identify the critical path.

Answer:

Three points will be deducted for each part not fully correct:

- Part 1: Diagram Construction & Labeling. ALL arrows must be present, including those connected to the Start and Finish circles.

- Part 2: Forward Calculation & Minimum Project Finish Time. ALL top numbers must be correct. The time must be stated in both the Finish circle AND the answer sentence.

- Part 3: Backward Calculation & Critical Path. ALL bottom numbers must be correct. ALL Critical Path arrows must be darkened in.  The Critical Path must be stated in correct order within the answer sentence.

3)  Emerald Isle Picnic Area & Grounds

The town of Emerald Isle is constructing a new picnic shelter and recreational grounds on a pristine site, and plans to use PERT / CPM analysis to manage the project based on the task information tabled below:

| Task | Duration | Prerequisite Tasks |
| --- | --- | --- |
| A) Clear grounds | 5 days | None |
| B) Construct road to shelter area | 3 days | None |
| C) Reclaim topsoil from grounds | 2 days | A |
| D) Build shelter complex | 7 days | B |
| E) Landscape shelter area & grounds | 4 days | C and D |
| F) Paint and wire shelter complex | 3 days | D |

Construct the PERT / CPM diagram for the Emerald Isle project, determine the minimum project finish time, and identify the critical path.

Answer:  	The minimum project finish time is 14 days and the critical path is B-D-E.

Three points will be deducted for each part not fully correct:

- Part 1: Diagram Construction & Labeling. ALL arrows must be present, including those connected to the Start and Finish circles.

- Part 2: Forward Calculation & Minimum Project Finish Time. ALL top numbers must be correct. The time must be stated in both the Finish circle AND the answer sentence.

- Part 3: Backward Calculation & Critical Path. ALL bottom numbers must be correct. ALL Critical Path arrows must be darkened in.  The Critical Path must be stated in correct order within the answer sentence.